## Tabelle1
Risk | Description | Prob. Of Occurrence | Damage | Mitigation Strategy | Person in Charge | Risk Factor (sort)
Complexity and Skills | Having missing overview and understanding of the codebase and thus struggeling with tasks | 50% | 6 | Bootcamps and peerprogramming | Nico | 3
Time Management | underestimate Issues thus taking way longer than expected | 70% | 4 | freetime is canceled | Nick | 2.8
Technologies | Having missing competence with the used technologies and thus strggeling with tasks | 30% | 6 | Bootcamps and peerprogramming | Willi | 1.8
(Bad) Architecture (Refractoring) | Making bad architectural decisions and thus having to refractor a lot | 10% | 7 | When unsure how to build something ask teammembers | Johannes | 0.7
Loss of Team members | Someone dropping out and thus loosing a lot of workforce | 2% | 10 | Team member still has to keep working on the project | Thomas | 0.2
Illness | Not getting work done due to illness | 5% | 2 | Try shifting the ill persons work to other teammembers | Thomas | 0.1